## Cover Page
KOGI STATE BUSINESS-ENABLING REFORM ACTION PLANS (BERAP) 2025
State: |  | KOGI
Reporting period: |  | FY 2025
SABER Focal Person: Mukadam Asiwaju Asiru Idris FCA | Hon Aliyu Nda Salami
List of contributing entities: | Ministry of Finance, Budget and Economic Planning, Ministry of Commerce and Industries, Ministry of Justice, State Judiciary, Kogi State Town Planning Board, Kogi State Internal Revenue Service, Land and Survey, Kogi State Investment Promotion and Public Private Partnership Agency (KOSIPPPPA), Kogi State Utility Infrastructure Management & Compliance Agency, Kogi State Geographic Information System, Kogi State Chamber of Commerce Mines & Industries (KOCCIMA).
URL Link to the published BERAP
Is this plan approved by the State Executive Council (SEC) |  |  | Yes | Choose as appropriate
If this was approved by SEC, please state date: |  |  | 20/12/24

## KOGI STATE ACTION PLAN
KOGI STATE 2024 BUSINESS ENABLING REFORM ACTION PLAN
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Responsible MDA | Contributing MDAs | List of Private Sector Contributors | Budget | Planned Start Date | Planned End Date
1 | Improved transparency and sustainability in the property registration and land investment process | 1. Identify the physical addresses of all Residences in a Classified Area/ settlements, including the physical addresses for Apartment Residents; 2. To attempt to locate the addresses for Persons who own the Residences, if they do not reside at the Residence; and 3. To attempt to locate individuals who previously resided at and/or owned a Residence within the Area during the Class. 4. Ensure Urban observatory, improve security of properties and live, aid physical planning and control, provision of physical infrastructures and a booster to revenue generation. 5. Digitize property database, online application and allocation. | 1. Sensitize property owners on the need for their property records to be registered on the Kogi State Geographic Information System (KOGIS) database. 2. Publishing Radio jingles, Social Media and fliers organizing town hall meetings. 3. Mapping/basemap of kogi state 4. Carry out Property identitfications implementation across the entire State, using mobile hand held devices with specialized application. 5. Training and deployment of adhoc staff. 6. Automation of Property database in the State. 7.Integration of property database with KGIRS payment portal. | To identify & capture 70% of landed properties {building and structures} Government and Private Properties: Including industries , hotels, plazas, Parks, Homes etc. | Bureau of Lands | Ministry of Housing and Urban Development, Kogi State Geographic Information System (KOGIS), Kogi State Internal Revenue Service (KGIRS), Kogi State Investment Promotion and Public Private Partnership Agency (KOSIPPPPA) , Town Planning & Development Board. | Kogi State Chamber of Commerce, Industry, Mines and Agriculture KOCCIMMA. Kogi State NGOs Network KONGONET Kogi State IGBO Traders Association Kogi State Igbo Community Association Nigeria Institute of Estate Surveyors (Kogi Chapter) National Union of Journalist NUJ (Kogi Chapter) Zenith Bank PLC Nigeria Bar Association NBA (Kogi Chapter) Nhub Nigeria Association of National Accountants of Nigeria (Kogi Chapter) Kogi State Traders Association | N500,000,000 | 2025-01-01 | 2025-12-01
2 | To Ease Fibre Optics Infrastructural Investments To Private Investors In Kogi State. | 1. Improve businesses access to internet , skills and up-to-date information. 2. Increase fibre optics deployment in Kogi State. | 1. Meeting with Telecom service providers, regulators and investors to increase Fibre optics deployment. 2. Registration of Investors; Liscensing of new telecom service providers and approval of permits for right of way. 3. Information management in respect of geographical Information system. 4.Training & capacity building of staff. 5. Development of a robust one-stop -shop website. | 1. Mapping of 250km of fibre optic cables routes and utility right of ways in conjunction with telecoms and other service providers. 2. Training of 20 staff on industry knowlegde. 3. Engage the services of a consultant to develop the agency website. | Kogi State Utility Infrastructure Management & Compliance Agency | Ministry of housing and urban development, Bureau of Lands, KGIRS, Kogi State Information and Technology Agency (Kogi SITDA). |  | N350,000,000 | 2025-01-01 | 2025-12-01
3 | Increased transparency of official fees and procedures | 1. Publish the approved fees and rates on the State website, Radio, Print and Electronic media for public awareness. 2. Establish a Greiviance redress mechanism for dispute resolution. | 1. Continuous enagagement/ enlightment of the public on the published laws, rates,fees, charges and procedures through social media platforms, radios and Television stations. 2. Activate the Grievance Redress Mechanism (GRM) to receive and address complains from Business operators and the general public. | 1. 144 slots of Radio and TV jingles for continous public awareness. 2. Atleast 52 sessions of GRM annually. | Ministry of Commerce and Industry | Kogi State Internal Revenue Service (KGIRS), Ministry of Justice, Kogi Chamber of Commerce Industry Mines & Agriculture (KOCCIMA) |  | N15,000,000 | 2025-02-01 | 2025-12-31
4 | Increased Transparency of fees & levies for inter-state trade and increased export certification | 1. Increase ease of doing business across the State using the state harmonized tax law. 2. Activate existing export promotion committee. 3. Establish taskforce to enforce compliance. | 1. Dismantle all illegal road blocks where produce levy are collected. 2. Encourage establisment of cooperative organizations. 3. Monitor warehouses for grading, sorting and certification of produces for exports | 1. Haulage Fees will be collected at the point of Loading and Offloading. 2. Export Certification will be fully automated. | Ministry of Commerce and Industry | KGIRS, KOCCIMA, Kogi State Commodity, Export Promotion and Market Development Agency, Ministry of Information and communication. |  | N50,000,000 | 2025-02-01 | 2025-12-12
5 | Simplified State and Local business tax regime | 1. Consolidate assessments of rates and levies between State and Local Government. 2. Enlighten the Public on harmonized rates and levies 3. Automate business premises registration and disputes resolution process | 1.The MOU between the KGIRS and the 21 Local Goverment will be redrafted to accomodate the consolidation of assessment of rates and levies. 2. Integration of Business Premises registration and dispute resolution process into the KGIRS portal. 3. Sensitization of the general public on harmonized rates and levies. | 1. Conclude MOU by end of first quarter 2025. 2. Integration done by Second quarter 2025. 3. Monthly town hall sensitisation meetings | KGIRS | Ministry of Local Government and Chieftaincy Affairs. Chairmen of the 21 Local Government & their Director of Local Govts. |  | N120,000,000 | 2025-01-01 | 2025-12-31
6 | Framework for Responsible and Inclusive Land Agricultural Investment (FRILIA) | 1. To enhance tenure governance by offering guidance and information on globally recognized techniques for managing and controlling the rights to use land, fisheries and forests. 2. To optimize transparency and boost efficiency of tenure systems in land intensive agricultural investments | 1. Sensitize stakeholders on globally recognized practices for tenor of land, fisheries and forests 2. Stakeholder engangement to foster continous dialogue and collaborations 3. Setting up greivance management system to address grievances araising from involuntary settlement, valuation, compemsation and others 4. Carry out community needs assesment and prepare community development plans to commit investors to CSR projects and mitigate projects impacts on existing community infrastructure. | 1. Prepare stakeholders engagement plan 2. Sensitization visits to 21 No first class traditional to communicate FRILIA tool kits 3. Identify and analyze stakeholders 4. Identify stakeholders issues and concerns 5. Conduct of 3No sensitization workshop (1No per Senatorial District) to communicate FRILIA tool kits 6. Set up greivance redress committee 7. Carryout community needs assesments in 10No project communities 8. Prepare 10No community development plans 9. Train 20 MoA staff on FRILIA knowledge area | Ministry of Agriculture | Bureau of Lands, KOSIPPPPA, KOGIS |  | N150,000,000 | 2025-01-01 | 2025-12-31
7 | Quick determination of commercial disputes | To Improve significantly the time spent to settle commercial disputes | 1. Establishment of Multi door Court House and more Small claims courts including acquisition of equipments. 2. Employment of skilled professionals and remuneration (at least 4 skilled arbitrators). 3.Remuneration of staff. 4. Public Awareness through Radio, print and electronic media. | 1. Establishments of two small claims courts. 2. Employment of 10 skilled staff. 3. Completion of 5 cases per month | The Judiciary | Ministry of Justice, Ministry of Commerce and Industry, KGIRS and KOCCIMA |  | N100,000,000 | 2025-01-01 | 2025-12-01