## Progress Report
STATE ACTION ON BUSINESS ENABLING REFORMS (SABER) PROGRESS REPORT
Original action plan as published | [9 empty] | Progress Update
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Responsible MDA | Contributing MDAs | Budget | Planned Start Date | Planned End Date | Status | Description of Status | Next Steps
1 | Improved transparency and sustainability in the property registration and land investment process | 1. identify the physical addresses of all Residences in a Classified Area/ settlements, including the physical addresses for Apartment Residents; 2. to attempt to locate the addresses for Persons who own the Residences, if they do not reside at the Residence; and 3. to attempt to locate individuals who previously resided at and/or owned a Residence within the Area during the Class. 4. Ensure Urban observatory, improve security of properties and live, aid physical planning and control, provision of physical infrastructures and a booster to revenue generation. | 1. Sensitize property owners on the need for their property records to be registered on the Kogi State Geographic Information System (KOGIS) database. 2. Publishing Radio jingles and fliers oragnizing town hall meetings 3. Carry out Property identitfications implementation across the entire State. | 1.Property Identification would be undertaken to identify the physical addresses of all Residences in a classified area/ settlements, including the persons who own the residences, or individuals who previously resided at and/or owned a residence within the area during the exercise. 2.The proposed Property identification program when implemented will ensure Urban observatory, improve security of live & properties, aid physical planning and control, and boost revenue generation. | Land and Survey | Kogi Stae Geographic Information System (KOGIS), Kogi Internal Revenue Service (KIRS), Kogi State Investment Promotion Agency (KOSIPA), | N115,000,000 | 2023-01-01 | 2023-12-01 | ONGOING: 1. Sensitization carrried out in three different centers which includes Felele, Zango and Ganaja in Lokoja metropolis. 2. 45000 Units of properties already captured. IMPACT: 1. The sensitisation carried will enlightened property owners on the importance of the renumeration exercise. 2. Increase the level of trust between propeerty owners and the authorities. 3. The execise when completetd will equip the State with a detailed database of properties for easy search and identification. | 1.STAKEHOLDER AWARENESS HAS BEEN CARRIED OUT. 2.PROPERTY IDENTIFICATION AND ENUMERATION STILL ONGOING CHALLENGES: 1. No Access to base map. 2. Adhoc staff carrying out the identification were poorly trained. 3. Some of the property owners were not willing to disclose necessary infomations. 4. No access to additional funding for completion of the identification exercise. | ACTION CARRIED OVER TO THE FOLLOWING YEAR: 1.Seeking to complete the property identificationand renumeration execrcise. 2.Acquire drones needed for property footprints capture for more identification. 3. Validate the existing data for the 45000 properties already captured.
2 | To Ease Fibre Optics Infrastructural Investments To Private Investors In Kogi State. | Improve businesses access to internet , skills and up-to-date information | Meeting with Network, providers, regulators and investors. Registration of Investors. Liscensing and Permits. Right of Way acquisition. Information Management in respect of geographical Information system. Price Regulation of unbound fibre products, Future Review. Training & capacity building of staff. Development of a robust one-stop -shop website. | Mapping of all routes for fibre cables and utility right of ways in conjunction with Network and other service providers. | Kogi State Utility Infrastructure Management & Compliance Agency | Kogi State Information and Technology Agency (Kogi SITDA), Ministry of Works, Land and Survey Town Planning Development Board. | N250,000,000 | 2024-01-01 | 2024-12-01 | ONGOING: Registration and liscensing of four major Telecomunication Companies, MTN, GLO, AIRTEL AND 9MOBILE. 19 Financial Intitutions has been sensitize by the Kogi State Utility infrstructure management and Compliance Agency (KUIMCA) introducing new fees and charges for erecting mast, pipelines, etc. IMPACT: | DELAYED DUE KOGI STATE 2023 GUBERNATORIAL ELECTION ACTIVITIES BUT STILL ONGOING: CHALLENGES: 1. Some operators not providing accurate information. 2. Too many discrepancy in the accurate length of fibre optics already laid. | ACTION CARRIED OVER TO THE FOLLOWING YEAR: 1. Sensitize more TELCOS for familiarisation with KUIMCA and the importance of registering under the agency. 2. Engage more auditors to audit existing fibre optics cable already laid. 3. Validate the Right of Way ROWprice of N145 per linear meter
3 | Increased transparency of official fees and procedures | Make the fees and rates charged as approved by State Tax Laws as amended in all revenue lines and are made known to the public and no hidden charges | The Laws, rates, fees and charges will be published in the State Website, Kogi State Government Websites and Newslettes of KGIRS, Intermittent publication and Media outing on Electronic media | All the fees that will be charged by the Ministry are contained in the State Harmonized Laws and these are the fees that will be published as contained in the Action steps | Ministry of Commerce and Industry | Kogi State Internal Revenue Service (KGIRS) | N5,000,000 | 2023-05-01 | 31/03/2023 | COMPLETED: 1. Rates and all fees to be charged are contatined in the harmonized laws. 2.The Laws, rates and fees has been published on official website. IMPACTS: 1. Engendered public confidence. 2.Improve Tax Compliance. | Significant aspect of this action plan has been completed. Laws, Fees and charges has been published on State website and KGIRS official website. MILESTONES: 1. Increase Revenue Generation. 2. Reduce trust deficit between taxpayers and collectors. | ACTION CARRIED OVER TO THE FOLLOWING YEAR: 1. Continous engagement of the public on social media and radio stations. 2. Quick dispute resolutions and reconciliation. 3. Establishment of 'KOGIREM' a Tax website platform for customers self assesment of tax payment.
4 | Increased Transparency of fees & levies for inter-state trade and increased export certification | Increase ease of doing business across the State | All road blocks across the State are to be dismantled as directed by the Executive Governor to ease the flow of goods and services across the states. | 1.Haulage Fees will be collected at the point of Loading and Offloading hence no road block will be allowed. 2. Export Certification has been fully automated, however, the use of the channel needs sensitization and awareness. 3. All illegal road blocks across the State must be demolished by the Law enforcement agents who will maintain free movement | Ministry of Commerce and Industry | State Vigillantee, police and Civil Defence, and Military, Ministry of Information and KGIRS | N20,000,000 | 2023-02-01 | 2023-12-12 | ONGOING: Committee has been set up to review prices of goods and commoditties withing the State. IMPLICATON: 1. The absence of road block for tax collection has eased the movement of goods and services in the State. | COMPLETED: 1.Highway roadblock for tax collection has been demolished 2.Haulage is being collected at point of Loading/Offloading. | ACTION CARRIED OVER TO THE FOLLOWING YEAR: 1. A committee has been set up for the review of prices of food and other commodities within the State. 2. We will also identify the prices of commodities in neigbouring States in comparative analysis with what is attainable in the State. 3. Report of the committee will be out in the 4th quarter of the year.
5 | Simplified State and Local business tax regime | Single tax body administering tax in the State. | 1.The expired MOU between the State IRS and the 21 Local Goverment will be renewed effective January 2023. 2. The MOU will be consolidated into permanenet Law such that all revenue will be administered by the KGIRS. 3. Local Government Revenue Officers will be subjected to competency test and those who are successful will be transferred to KGIRS as Staff while the unsucessful will be moved to another department of the Local Governement. 4.A joint account where DLG and Treasurer will be signatories but a confirmation from KGIRS is made before withdrawal by the Local Government. 5. Monthly Revenue Performance meeting to be chaired by the KGIRS and Minstry of Local Government with 21 Local Government Chairmen and Treasurers as Participants will happen monthly 6. All cash collection is to be outlawed. | The reform is focused on achieving simplified tax regime that will lead to increase in IGR for both the State and the Local Government | KGIRS | Ministry of Local Government and Chieftaincy Affairs, Chairmen of the 21 Local Government | N20,000,000 | 1st January, 2023 | 12th Dec,2023 | ONGOING: MOU yet to be signed but has been reviewed and sent to the LGs. IMPLICATION: 1. Reduce the issues of multiple taxation and its impact of prices of comoditties. | ONGOING: JOINT TAX MEETING HAS BEEN HELD BUT MOU YET TO BE RENEWED BUT PLANS ARE ON. CHALLENGES: 1. Dificulties in Management of FORUM of revenue services and the Local government officials. 2. Dificulties in getting the seamless buy in of major stakeholders. | ACTION CARRIED OVER TO THE FOLLOWING YEAR: 1. Reviewed MOU will be signed this year. Organizing competency test for the Local Government revenue officers. 2. Organising adequate trainings.
6 | Improve domestic and external trade competitiveness | Quality improvement on all products in the state with special focus on Cashew nut production and reduced cost of labour. | 1.Cashew producing farmers will be supervised by Extension workers to ensure quality harvest. 2. We will create enabling environment for Standard Organization of Nigeria to operate freely to gurantee quality 3.Grants/Aids will be given to farmers and traders through Ministry of Commmerce to qualIfying Individual or Company | Improved Quality of goods and services through Supervision of production and motivation through grants/Aids by the State. | Ministry of Commerce and Industry | Ministry of Finance, and Ministry of Agricluture | N5OO,OOO,OOO | 2023-01-01 | 2023-10-01 | ONGOING: 1. Grants and financial aids farmers and traders. 2.7000 hectares of land cleared and fully tractorized in 76 clusters for cultivation of Cassava, Rice and other crops. IMPACT: 1. Food avalability. 2. Reduction in food inflation rates. | ONGOING: MINISTRY OF AGRICULTURE HAS TAKEN CHARGE OF EXPORT CERTIFICATION. CHALLENGES: Operationalisation of the new agencies to perfect all the reform objectives. | ACTION STEPS CARRIED OVER TO THE FOLLOWING YEAR: 1. Constitution of members of new agencies like Agro-Allied, Commodity Exchange and Export Agency.
7 | Harmonized and more transparent State taxes | Harmonize Local Government taxes with that of the State so as to inmprove the ease of doing business, to also increase revenue accountability and increase in IGR for both state and Local Government | The State Tax Laws and the Local Governemt Revenue Laws should be merged into one document and published on the State and IRS websites . | KGIRS *After harmonization, KGIRS will be collecting tenement fees, radio and television license for the 21 Local Governments . Harmonization of tax laws with the Local Government: in addition to the other lines of revenue, Emblem is a collection of state and Local Government. This will be harmonized in the year 2023 with State IRS collecting and sharing formula will be put in place between the state and the 21 Local Government Council. | Ministry of Commerce and Industries, State House of assembly | 21 LG Chairmen | N5,000,000 | 2023-01-01 | Nov, 2023 | ONGOING: 1. The Revenue harmonization law has been passed. 2. The impact is the reduction of taxes due to multiple taxations. | COMPLETED: TAX COLLECTION HARMONIZED, THE KOGI STATE INTERNAL REVENUE SERVICES HAVE TAKEN OVER COLLECTION OF TENERMENT RATE,CITIZENSHIP AND TRANSPORTATION (PARK LEVY) | ACTION CARRIED OVER TO THE FOLLOWING YEAR: 1. Process of Tax Review domestication of the outcome of the presidential tax and fiscal policy review committee. 2. Ensure the MOU Signed with LGs as soon as possible.
8 | Quick determination of commercial disputes | Improve significantly the time spend to settle commercial disputes | 1. Establishment of Multi door Court House, Including acquisition of equipments. 2. Employment of skilled professionals and remuneration (at least 4 skilled arbitrators). 3.Remuneration of staff. 4. Public Awareness | Real Estates, Industries, Government, Civil Servants, Businesses, Farmers, Traders Target Objectives: 1. Multi door Court House is open to all manner of people in business community including artisans, petty trader, partnerships, Limited and Public Liability Companies that are involved in some forms of commercial disputes in the course of their transactions desiring quick determination of such disputes within Kogi State. 2. Employment opportunities to qualified arbitrators, reconciliatory, mediators and negotiators who are indigenes of Kogi State. 3. Employment opportunities to qualified administrative personnel, personal assistant, Secretaries, ICT personnel and other sundry staff. 4. Filling fees charged or penalties awarded against any party for defaults can generate substantial revenue for the Kogi State government | Ministry of Justice | Ministry of Commerce and Industry, High Court of justice , National Industrial Court, Taxes Appeal Tribunal . | N712,000,000 | 2023-01-01 | 2023-12-01 | ONGOING: MINISTRY OF JUSTICE HAS SENSITIZE STAKEHOLDERS ON ESTABLISHMENT OF MULTIDOOR COURT HOUSES FOR QUICK DETERMINATION OF DISPUTES. IMPACT; When completed the Multidoor court houses will support businessess in getting uick timely and well deserved resolutions of conflicts and other related matters. | DELAYED DUE KOGI STATE 2023 GUBERNATORIAL ELECTION ACTIVITIES | ACTION CARRIED OVER TO THE FOLLOWING YEAR: 1. Establishment of Multidoor court houses for quick dispute resolution. 2. Continous engagement with the public and creating more awarenesss.
9 | Establishment of a skills registry and talent development | 1. Creation of a pool of knowledgeable and skilled manpower that will facilitate eGovernment practices, technology acquisition, assimilation and diffusion in public service; Increase in productivity of workforce via digital literacy. 2. Solving the conundrum around inadequacies in preparing current and potential workforce for digital economy and foster in them: • General skills for creativity • Interpersonal skills and ability to execute plans • High standards and independence • Natural inclination to further learning • Skills for relevance and competitiveness in 21st Century 3. Establishment of proficiency of workforce in digital literacy to guide policy formulation 4. Growing of economy through a vibrant ICT Sector that contributes to increased revenue; 5. Stimulation and optimization of investment and enterprise environment; 6. Development of a knowledge-based economy that is rooted in sustained human capacity development, wealth generation and job creation; 7. Improvement of operational efficiencies across government and economy-wide. | 1. Conduct of baseline assessment to establish proficiency of potential and current workforce digital literacy using the ICT Digital Literacy metrics 2. Development of Digital Literacy Strategy to bridge the identify gaps; Formulation of Policy, Setting of Standard and Guidelines 3. Development of Digital Literacy Framework and Career Certification Roadmap for - Review of curriculum at all levels of, development of framework /mapping of career and capacity skills development standards into all categories of academic programmes and levels of education and continuous professional development of all categories of workforce; 4. Establishment, Setting Up and Activation of Centers for Development of Digital Literacy and Emerging Skills as testing and certification Centers in the 6 zones of Kogi State; Implementation of Framework 5. Training and certification of all workforce at Project Office, zonal Project Offices in minimum of 3 and maximum of 5 skill areas starting with IC3 Digital Literacy in the first year; 6. Training and certification of trainers in minimum of 3 and maximum of 5 skill areas starting with IC3 Digital Literacy in the first year; | All current public service workforce, regardless of career, level or job role All Potential workforce; graduate and non-graduate job seekers; unemployed or underemployed Small and medium scale businesses. Target Objectives: Build capacity in all participants using digital tool for ease of their businesses. Apply digital tools to gather, evaluate, and use information for the ease of businesses. • Employ strategies to guide inquiry in digital environments. • Use digital tools according to disciplinary conventions and in application to business processes. • Engage proactively with digital tools in business environments. • Apply existing knowledge to generate new ideas, products, or processes in digital representation of businesses. • Use critical thinking skills to plan and conduct research, manage projects, solve problems, and make informed decisions using appropriate digital tools and resources. • Process digital data and report results. | Kogi Enterprise Development Agency and Kogi State Information and Technology Agency (Kogi SITDA) | Kogi State Ministry of Finance, Budget & Economic Planning, Kogi State Investment Promotion Agency (KOSIPA) | N563,137,259 | 2023-01-16 | 2023-10-27 | YET TO COMMENCE | DELAYED DUE KOGI STATE 2023 GUBERNATORIAL ELECTION ACTIVITIES. CHALLENGES; 1. Full operationalization of the agency is yet to commence. 2. Anew DG to head the agency yet to be appointed. | ACTION CARRIED OVER TO THE FOLLOWING YEAR. 1. Ensure quick appointment of a new DG for the agency. 2.Ensure full operationaliztion of the Kogi State Information and Technology Agency (Kogi SITDA)..